## Sprint1 document
Tasks/Features | Hours | Assign to | Actual | Impact |  |  | Total
Logging Research and Design | 16 | Michell | 0 | 0 |  | Michell | 42
AuthZ Research and Design | 16 | Jacen | 0 | 0 |  | Jacen | 42
Data Store Archiving Research and Design | 26 | Jake | 0 | 0 |  | Jake | 31
Flat File Archiving Research and Design | 16 | Albert | 11.5 | 6.5 |  | Albert | 26
Revise BRD (V.2) | 26 | Jacen | 0 | 0 |  | Peter | 36
Revise Tech Spec (V.2) | 26 | Michell | 24 | 18 |  | Daniel | 26
Revise Design Document (V.2) | 10 | Peter | 2 | 0
Revise Project Plan (V.2) | 10 | Albert | 15 | 10 |  | Start Date | End Date
Revise Project Roadmap (V.2) | 1 | Jake | 0 | 0 |  | 2019-10-18 | 2019-10-30
Revise Sitemaps (V.2) | 4 | Jake | 0 | 0
AuthN Research and Design | 26 | Peter | 0 | 0
Error Handling Research and Design | 26 | Daniel | 0 | 0
Total Velocity | 203 | Actuall | 52.5 | Impact | 34.5 | Actuall/Planned | 74.14% | Impact/Planned | 82.5%

## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2019-10-17 | 0 | 42 | 42 | 0 | 42 | 42 | 0 | 26 | 26 | 0 | 36 | 36 | 0 | 26 | 26 | 0 | 31 | 31 | 203 | 203
2019-10-18 | 2 | 40 | 38.8 | 0 | 42 | 38.8 | 0 | 26 | 24 | 0 | 36 | 33.2 | 3 | 25 | 24 | 1 | 31 | 28.6 | 200 | 186.8
2019-10-19 | 4 | 38 | 35.6 | 2 | 41 | 35.6 | 0 | 26 | 22 | 0 | 36 | 30.4 | 0 | 25 | 22 | 1 | 30 | 26.2 | 196 | 170.6
2019-10-20 | 0 | 38 | 32.4 | 2 | 40 | 32.4 | 0 | 26 | 20 | 2 | 34 | 27.6 | 1 | 25 | 20 | 0 | 30 | 23.8 | 193 | 154.4
2019-10-21 | 1 | 37 | 29.2 | 3 | 39 | 29.2 | 2 | 24 | 18 | 0 | 34 | 24.8 | 0 | 25 | 18 | 1 | 29 | 21.4 | 188 | 138.2
2019-10-22 | 3 | 34 | 26 | 0 | 39 | 26 | 3 | 21 | 16 | 0 | 34 | 22 | 0 | 25 | 16 | 0 | 29 | 19 | 182 | 122
2019-10-23 | 1 | 33 | 22.8 | 0 | 39 | 22.8 | 3 | 18.5 | 14 | 0 | 34 | 19.2 | 0 | 25 | 14 | 2 | 27 | 16.6 | 176.5 | 105.8
2019-10-24 | 2 | 31 | 19.6 | 0 | 39 | 19.6 | 3 | 18 | 12 | 0 | 34 | 16.4 | 0 | 25 | 12 | 0 | 27 | 14.2 | 174 | 89.6
2019-10-25 | 0 | 31 | 16.4 | 0 | 39 | 16.4 | 4 | 16 | 10 | 0 | 34 | 13.6 | 0 | 25 | 10 | 0 | 27 | 11.8 | 172 | 73.4
2019-10-26 | 4 | 28 | 13.2 | 0 | 39 | 13.2 | 2 | 15 | 8 | 0 | 34 | 10.8 | 0 | 25 | 8 | 0 | 27 | 9.4 | 168 | 57.2
2019-10-27 | 3 | 26 | 10 | 0 | 39 | 10 | 2 | 14 | 6 | 0 | 34 | 8 | 0 | 25 | 6 | 0 | 27 | 7 | 165 | 41
2019-10-28 | 2 | 25 | 6.8 | 0 | 39 | 6.8 | 2 | 13 | 4 | 0 | 34 | 5.2 | 0 | 25 | 4 | 0 | 27 | 4.6 | 163 | 24.8
2019-10-29 | 2 | 24 | 3.6 | 0 | 39 | 3.6 | 3.5 | 11.5 | 2 | 0 | 34 | 2.4 | 0 | 25 | 2 | 0 | 27 | 2.2 | 160.5 | 8.6
2019-10-30 | 0 | 24 | 0 | 0 | 39 | 0 | 2 | 9.5 | 0 | 0 | 34 | 0 | 0 | 25 | 0 | 0 | 27 | 0 | 158.5 | 0
2019-10-31 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
ExpectedTotal Hour | 42 |  |  | 42 |  |  | 26 |  |  | 36 |  |  | 26 |  |  | 31 |  |  | 203
Hour per Day | 3.2 |  |  | 3.2 |  |  | 2 |  |  | 2.8 |  |  | 2 |  |  | 2.4 |  |  | 15.6

## KanBan Board
To Do | In progress | Testing | Blocked | Done
Logging Research and Design | Michell
AuthZ Research and Design
Data Store Archiving Research and Design
Flat File Archiving Research and Design | Albert
Revise BRD (V.2) | Jacen
Revise Tech Spec (V.2) | Michell
Revise Design Document (V.2) | Peter
Revise Project Plan (V.2) |  |  |  | Albert
Revise Project Roadmap (V.2) | Joshua
Revise Sitemaps (V.2)
AuthN Research and Design
Error Handling Research and Design