## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2020-01-27 | 0 | 22 | 22 | 0 | 8 | 8 | 0 | 26 | 26 | 0 | 8 | 8 | 0 | 10 | 10 | 0 | 16 | 16 | 90 | 90
2020-01-28 | 1 | 21 | 20.4286 | 0 | 8 | 7.4286 | 4 | 24 | 24.1429 | 0 | 8 | 7.4286 | 0 | 10 | 9.2857 | 0 | 16 | 14.8571 | 87 | 83.5714
2020-01-29 | 1 | 21 | 18.8571 | 0 | 8 | 6.8571 | 2 | 23 | 22.2857 | 0 | 8 | 6.8571 | 0 | 10 | 8.5714 | 1 | 15 | 13.7143 | 85 | 77.1429
2020-01-30 | 2 | 19 | 17.2857 | 0 | 8 | 6.2857 | 4 | 19 | 20.4286 | 0 | 8 | 6.2857 | 0 | 10 | 7.8571 | 0 | 15 | 12.5714 | 79 | 70.7143
2020-01-31 | 0 | 19 | 15.7143 | 0 | 8 | 5.7143 | 2 | 17 | 18.5714 | 0 | 8 | 5.7143 | 0 | 10 | 7.1429 | 1 | 14 | 11.4286 | 76 | 64.2857
2020-02-01 | 3 | 17 | 14.1429 | 0 | 8 | 5.1429 | 0 | 17 | 16.7143 | 0 | 8 | 5.1429 | 0 | 10 | 6.4286 | 0 | 14 | 10.2857 | 74 | 57.8571
2020-02-02 | 1 | 16 | 12.5714 | 0 | 8 | 4.5714 | 2 | 14 | 14.8571 | 0 | 8 | 4.5714 | 0 | 10 | 5.7143 | 2 | 12 | 9.1429 | 68 | 51.4286
2020-02-03 | 0 | 16 | 11 | 0 | 8 | 4 | 0 | 14 | 13 | 0 | 8 | 4 | 0 | 10 | 5 | 0 | 12 | 8 | 68 | 45
2020-02-04 | 0 | 16 | 9.4286 | 0 | 8 | 3.4286 | 4 | 10 | 11.1429 | 0 | 8 | 3.4286 | 0 | 10 | 4.2857 | 3 | 9 | 6.8571 | 61 | 38.5714
2020-02-05 | 2 | 16 | 7.8571 | 0 | 8 | 2.8571 | 0 | 10 | 9.2857 | 0 | 8 | 2.8571 | 0 | 10 | 3.5714 | 1 | 8 | 5.7143 | 60 | 32.1429
2020-02-06 | 0 | 16 | 6.2857 | 0 | 8 | 2.2857 | 0 | 10 | 7.4286 | 0 | 8 | 2.2857 | 0 | 10 | 2.8571 | 1 | 7 | 4.5714 | 59 | 25.7143
2020-02-07 | 4 | 14 | 4.7143 | 0 | 8 | 1.7143 | 0 | 10 | 5.5714 | 0 | 8 | 1.7143 | 0 | 10 | 2.1429 | 0 | 7 | 3.4286 | 57 | 19.2857
2020-02-08 | 0 | 12 | 3.1429 | 0 | 8 | 1.1429 | 0 | 10 | 3.7143 | 2 | 6 | 1.1429 | 0 | 10 | 1.4286 | 2 | 5 | 2.2857 | 51 | 12.8571
2020-02-09 | 4 | 10 | 1.5714 | 0 | 8 | 0.57143 | 2 | 8 | 1.8571 | 0 | 6 | 0.57143 | 0 | 10 | 0.71429 | 0 | 5 | 1.1429 | 47 | 6.4286
2020-02-10 | 2 | 10 | 0 | 0 | 8 | 0 | 4 | 6 | 0 | 0 | 6 | 0 | 0 | 10 | 0 | 1 | 4 | 0 | 44 | 0
2020-02-11 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
Expected Total Hour | 22 |  |  | 8 |  |  | 26 |  |  | 8 |  |  | 10 |  |  | 16 |  |  | 90
Expected Hour per Day | 1.5714 |  |  | 0.57143 |  |  | 1.8571 |  |  | 0.57143 |  |  | 0.71429 |  |  | 1.1429 |  |  | 6.4286

## Tasks
Tasks/Features | Hours | Assign to | Actual | Impact | Ratio |  | Total
AuthZ Rework | 8 | Jacen | 0 | 0 | #DIV/0! | Jacen | 8
Cloud Database | 16 | Albert | 14 | 12 | 0.85714 | Jake | 16
Registration rework | 4 | Albert | 4 | 4 | 1 | Albert | 15
Create Account rework | 6 | Albert | 5 | 5 | 1 | Peter | 8
Enable/Disable Account | 4 | Daniel | 0 | 0 | #DIV/0! | Michell | 22
Data Masking AuthN | 10 | Jake | 7 | 5 | 0.71429 | Daniel | 7
Update Account | 6 | Daniel | 0 | 0 | #DIV/0! | velocity capacity | 0 | hrs/person
AuthN Rework | 8 | Peter | 2 | 2 | 1 |  | 40 | hrs total
Reorganize Project | 4 | Michell | 7 | 4
Create User Session | 8 | Michell | 6 | 4
Delete Account Rework | 6 | Jake | 5 | 5
User Profile | 10 | Michell | 5 | 2
Total Velocity | 62 | Actual Hours | 32 | Impact Hours | 28 | Actual/Planned | 48.39% | Impact/Planned | 54.84%

## KanBan Board
To Do | In progress | Testing | Blocked | Done
Michell
Jacen
Delete User Rework | Joshua
Cloud Database |  |  | Albert
Create Account rework |  | Albert
Registration Rework |  |  |  | Albert
Daniel
Michell
Michell
Authn Data Masking | Joshua
Jacen
Peter
Daniel
Peter