## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2019-10-31 | 0 | 28 | 28 | 0 | 31 | 31 | 0 | 28 | 28 | 0 | 29 | 29 | 0 | 25 | 25 | 0 | 31 | 31 | 172 | 172
2019-11-01 | 3 | 26 | 25.85 | 0 | 31 | 28.62 | 1 | 27 | 25.85 | 1 | 28 | 26.77 | 0 | 25 | 23.08 | 1 | 30 | 28.62 | 167 | 158.79
2019-11-02 | 0 | 26 | 23.7 | 2 | 29 | 26.24 | 1 | 26 | 23.7 | 0 | 28 | 24.54 | 0 | 25 | 21.16 | 0 | 30 | 26.24 | 164 | 145.58
2019-11-03 | 2.5 | 24 | 21.55 | 2 | 27 | 23.86 | 1 | 25 | 21.55 | 2 | 26 | 22.31 | 3 | 23 | 19.24 | 0 | 30 | 23.86 | 155 | 132.37
2019-11-04 | 0 | 24 | 19.4 | 3 | 24 | 21.48 | 2 | 24 | 19.4 | 2 | 24 | 20.08 | 1 | 23 | 17.32 | 2 | 28 | 21.48 | 147 | 119.16
2019-11-05 | 3 | 21 | 17.25 | 0 | 24 | 19.1 | 2.5 | 22.5 | 17.25 | 3 | 22 | 17.85 | 1 | 22 | 15.4 | 2 | 26 | 19.1 | 137.5 | 105.95
2019-11-06 | 2 | 20 | 15.1 | 0 | 24 | 16.72 | 1.5 | 21 | 15.1 | 0 | 22 | 15.62 | 0 | 22 | 13.48 | 1.5 | 24.5 | 16.72 | 133.5 | 92.74
2019-11-07 | 1 | 19 | 12.95 | 0 | 24 | 14.34 | 2 | 19 | 12.95 | 0 | 22 | 13.39 | 0 | 22 | 11.56 | 2 | 22.5 | 14.34 | 128.5 | 79.53
2019-11-08 | 2 | 17 | 10.8 | 0 | 24 | 11.96 | 3 | 16 | 10.8 | 0 | 22 | 11.16 | 0 | 22 | 9.64 | 3 | 19.5 | 11.96 | 120.5 | 66.32
2019-11-09 | 3 | 16 | 8.65 | 0 | 24 | 9.58 | 2 | 14 | 8.65 | 0 | 22 | 8.93 | 0 | 22 | 7.72 | 2 | 17.5 | 9.58 | 115.5 | 53.11
2019-11-10 | 4.5 | 12 | 6.5 | 4 | 20 | 7.2 | 2 | 8 | 6.5 | 0 | 22 | 6.7 | 4.5 | 17.5 | 5.8 | 4.5 | 13 | 7.2 | 92.5 | 39.9
2019-11-11 | 3 | 10 | 4.35 | 8 | 12 | 4.82 | 3 | 5 | 4.35 | 0 | 22 | 4.47 | 1 | 16.5 | 3.88 | 4 | 9 | 4.82 | 74.5 | 26.69
2019-11-12 | 1 | 9 | 2.2 | 0 | 12 | 2.44 | 2 | 3 | 2.2 | 3 | 19 | 2.24 | 0 | 16.5 | 1.96 | 2 | 7 | 2.44 | 66.5 | 13.48
2019-11-13 | 5 | 6 | 0 | 0 | 12 | 0.06 | 4 | 0 | 0.05 | 0 | 19 | 0.01 | 0 | 16.5 | 0.04 | 3 | 4 | 0.06 | 57.5 | 0.27
2019-11-14 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
Expected Total Hour | 28 |  |  | 31 |  |  | 28 |  |  | 29 |  |  | 25 |  |  | 31 |  |  | 172
Expected Hour per Day | 2.15 |  |  | 2.38 |  |  | 2.15 |  |  | 2.23 |  |  | 1.92 |  |  | 2.38 |  |  | 13.21

## Tasks
Tasks/Features | Hours | Assign to | Actual | Impact | Ratio |  | Total
Logging Research and Design | 16 | Michell | 9.5 | 5 |  | Michell | 28
AuthZ Research and Design | 13 | Jacen | 7 | 5 |  | Jacen | 31
Data Store Logging Research and Design | 26 | Jake | 4.5 | 3 |  | Jake | 31
Flat File Archiving Research and Design | 14 | Albert | 16.5 | 14 |  | Albert | 28
Revise BRD (V.2) | 18 | Jacen | 16 | 16 |  | Peter | 29
Revise Tech Spec (V.2) | 12 | Michell | 17.5 | 14 |  | Daniel | 25
Revise Design Document (V.2) | 8 | Peter | 8 | 7 |  |  | 172
Review Core Requirements | 4 | Albert | 4 | 4 |  | Start Date | End Date
Revise Project Roadmap (V.2) | 1 | Jake | 1 | 0.5 |  | 2019-01-11 | 11-13-2019
Revise Sitemaps (V.2) | 4 | Jake | 8 | 7 |  | 172 | try best to reach | 32.5/person
AuthN Research and Design | 21 | Peter | 3 | 3
Error Handling Research and Design | 25 | Daniel | 9.5 | 8.5
Network Diagram | 10 | Albert | 10.5 | 10
Total Velocity | 172 | Actual Hours | 115 | Impact | 97 | Actual/Planned | 33.14% | Impact/Planned | 43.6%

## KanBan Board
To Do | In progress | Testing | Blocked | Done
Logging Research and Design | Michell
AuthZ Research and Design | Jacen
Data Store Logging Research and Design | Joshua
Flat File Archiving Research and Design |  |  |  | Draft Finished - Albert
Revise BRD (V.2) |  |  |  | Jacen
Revise Tech Spec (V.2) |  |  |  | Michell
Revise Design Document (V.2) |  |  |  | Complete
Review Core Requirements |  |  |  | Complete
Revise Project Roadmap (V.2) |  |  |  | Joshua
Revise Sitemaps (V.2) |  |  |  | Complete
AuthN Research and Design | Peter
Error Handling Research and Design | Daniel
Network Diagram |  |  |  | Draft Finished - Albert