## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2019-11-14 | 0 | 41 | 41 | 0 | 47 | 47 | 0 | 38 | 38 | 0 | 41 | 41 | 0 | 46 | 46 | 0 | 43 | 43 | 256 | 256
2019-11-15 | 4 | 40 | 37.8462 | 0 | 47 | 43.3846 | 0 | 38 | 35.0769 | 0 | 41 | 37.8462 | 4 | 43 | 42.4615 | 1 | 42 | 39.6923 | 251 | 236.3077
2019-11-16 | 3.5 | 38 | 34.6923 | 0 | 47 | 39.7692 | 0 | 38 | 32.1538 | 0 | 41 | 34.6923 | 6 | 38 | 38.9231 | 0 | 42 | 36.3846 | 244 | 216.6154
2019-11-17 | 4 | 34 | 31.5385 | 0 | 47 | 36.1538 | 4 | 34 | 29.2308 | 3 | 38 | 31.5385 | 0 | 38 | 35.3846 | 6 | 37 | 33.0769 | 228 | 196.9231
2019-11-18 | 0 | 34 | 28.3846 | 0 | 47 | 32.5385 | 1 | 33 | 26.3077 | 1 | 37 | 28.3846 | 0 | 38 | 31.8462 | 0 | 37 | 29.7692 | 226 | 177.2308
2019-11-19 | 0 | 34 | 25.2308 | 3 | 44 | 28.9231 | 4 | 29 | 23.3846 | 0 | 37 | 25.2308 | 2 | 36 | 28.3077 | 2 | 35 | 26.4615 | 215 | 157.5385
2019-11-20 | 3 | 31 | 22.0769 | 0 | 44 | 25.3077 | 0 | 29 | 20.4615 | 0 | 37 | 22.0769 | 0 | 36 | 24.7692 | 0 | 35 | 23.1538 | 212 | 137.8462
2019-11-21 | 0 | 31 | 18.9231 | 4 | 40 | 21.6923 | 6 | 23 | 17.5385 | 0 | 37 | 18.9231 | 0 | 36 | 21.2308 | 4 | 31.5 | 19.8462 | 198.5 | 118.1538
2019-11-22 | 7 | 25 | 15.7692 | 0 | 40 | 18.0769 | 0 | 23 | 14.6154 | 6 | 31 | 15.7692 | 7.5 | 31 | 17.6923 | 8 | 24.5 | 16.5385 | 174.5 | 98.4615
2019-11-23 | 5 | 24 | 12.6154 | 0 | 40 | 14.4615 | 0 | 23 | 11.6923 | 0 | 31 | 12.6154 | 0 | 31 | 14.1538 | 5 | 20 | 13.2308 | 169 | 78.7692
2019-11-24 | 10 | 17 | 9.4615 | 4 | 37 | 10.8462 | 10 | 13 | 8.7692 | 7 | 24 | 9.4615 | 9.5 | 26 | 10.6154 | 10 | 13 | 9.9231 | 130 | 59.0769
2019-11-25 | 4 | 13 | 6.3077 | 8 | 32 | 7.2308 | 0 | 13 | 5.8462 | 0 | 24 | 6.3077 | 0 | 26 | 7.0769 | 4 | 11 | 6.6154 | 119 | 39.3846
2019-11-26 | 3 | 11 | 3.1538 | 4 | 29 | 3.6154 | 3 | 10 | 2.9231 | 2 | 22 | 3.1538 | 0 | 26 | 3.5385 | 3 | 10 | 3.3077 | 108 | 19.6923
2019-11-27 | 0 | 11 | 0 | 0 | 40 | 0 | 2 | 8 | 0 | 2 | 20 | 0 | 0 | 26 | 0 | 0 | 10 | 0 | 115 | 0
2019-11-28 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
Expected Total Hour | 41 |  |  | 47 |  |  | 38 |  |  | 41 |  |  | 46 |  |  | 43 |  |  | 256
Expected Hour per Day | 3.1538 |  |  | 3.6154 |  |  | 2.9231 |  |  | 3.1538 |  |  | 3.5385 |  |  | 3.3077 |  |  | 19.6923

## Tasks
Tasks/Features | Hours | Assign to | Actual | Impact | Ratio |  | Total
Flat File Logging Research and Design | 15 | Michell | 21.5 | 16 |  | Michell | 41
AuthZ Research and Design | 5 | Jacen | 18 | 2 |  | Jacen | 47
Data Store Logging Research and Design | 8 | Jake | 18 | 15.5 |  | Jake | 43
Flat File Archiving Research and Design | 12 | Albert | 12 | 12 |  | Albert | 38
AuthN Research and Design | 15 | Peter | 9 | 9 |  | Peter | 41
Error Handling Research and Design | 20 | Daniel | 15 | 13 |  | Daniel | 46
Flat File Logging Implementation and Testing | 26 | Michell | 19 | 12 |  |  | 256
AuthZ Implementation and Testing | 42 | Jacen | 0 | 0 |  | Start Date | End Date
Data Store Logging Implementation and Testing | 35 | Jake | 21 | 16 |  | 11-15-2019 | 12-27-2019
Flat File Archiving Implementation and Testing | 26 | Albert | 19 | 19
AuthN Implementation and Testing | 26 | Peter | 12 | 12 |  | velocity capacity | 52hrs / person
Error Handling Implementation and Testing | 26 | Daniel | 5 | 5
|  |  | 0 | 0
Total Velocity | 256 | Actual Hours | 169.5 | Impact | 131.5 | Actual/Planned | 33.79% | Impact/Planned | 48.63%

## KanBan Board
To Do | In progress | Testing | Blocked | Done
Logging Research and Design | Michell
AuthZ Research and Design | Jacen
Data Store Logging Research and Design |  |  |  | Joshua
Flat File Archiving Research and Design |  |  |  | Albert
AuthN Research and Design |  |  |  | Peter
Error Handling Research and Design | Daniel
Flat File Logging Implementation and Design | Michell
AuthZ Implementation and Design | Jacen
Data Store Logging Implementation and Design |  | Joshua
Flat File Archiving Implementation and Design |  | Albert
AuthN Implementation and Design | Peter
Error Handling Implementation and Design | Daniel