## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2019-11-29 | 2 | 31 | 32 | 4 | 28 | 32 | 0 | 32 | 32 | 0 | 32 | 32 | 3 | 29 | 32 | 1 | 31 | 32 | 183 | 192
2019-11-30 | 0 | 32 | 29.5385 | 3 | 26 | 29.5385 | 2 | 30 | 29.5385 | 0 | 32 | 29.5385 | 4 | 27 | 29.5385 | 0 | 31 | 29.5385 | 178 | 177.2308
2019-12-01 | 3 | 29 | 27.0769 | 4 | 24 | 27.0769 | 0 | 30 | 27.0769 | 0 | 32 | 27.0769 | 0 | 27 | 27.0769 | 2 | 29 | 27.0769 | 171 | 162.4615
2019-12-02 | 1 | 28 | 24.6154 | 8 | 16 | 24.6154 | 4 | 26 | 24.6154 | 0 | 32 | 24.6154 | 0 | 27 | 24.6154 | 0 | 29 | 24.6154 | 158 | 147.6923
2019-12-03 | 0 | 28 | 22.1538 | 10 | 4 | 22.1538 | 5 | 21 | 22.1538 | 0 | 32 | 22.1538 | 6 | 23 | 22.1538 | 3 | 26 | 22.1538 | 134 | 132.9231
2019-12-04 | 0 | 28 | 19.6923 | 0 | 4 | 19.6923 | 0 | 21 | 19.6923 | 0 | 32 | 19.6923 | 0 | 23 | 19.6923 | 0 | 26 | 19.6923 | 134 | 118.1538
2019-12-05 | 1 | 27 | 17.2308 | 0 | 4 | 17.2308 | 0 | 21 | 17.2308 | 0 | 32 | 17.2308 | 2 | 21 | 17.2308 | 4 | 22 | 17.2308 | 127 | 103.3846
2019-12-06 | 0 | 27 | 14.7692 | 0 | 4 | 14.7692 | 0 | 21 | 14.7692 | 0 | 32 | 14.7692 | 6 | 17 | 14.7692 | 0 | 22 | 14.7692 | 123 | 88.6154
2019-12-07 | 2 | 25 | 12.3077 | 0 | 4 | 12.3077 | 4 | 17 | 12.3077 | 2 | 30 | 12.3077 | 0 | 17 | 12.3077 | 2 | 20 | 12.3077 | 113 | 73.8462
2019-12-08 | 0 | 25 | 9.8462 | 0 | 4 | 9.8462 | 2 | 21 | 9.8462 | 2 | 28 | 9.8462 | 3 | 17 | 9.8462 | 0 | 20 | 9.8462 | 115 | 59.0769
2019-12-09 | 0 | 25 | 7.3846 | 0 | 4 | 7.3846 | 0 | 21 | 7.3846 | 0 | 28 | 7.3846 | 0 | 17 | 7.3846 | 1 | 19 | 7.3846 | 114 | 44.3077
2019-12-10 | 0 | 25 | 4.9231 | 0 | 4 | 4.9231 | 7.5 | 13.5 | 4.9231 | 0 | 28 | 4.9231 | 4 | 13 | 4.9231 | 3 | 16 | 4.9231 | 99.5 | 29.5385
2019-12-11 | 4 | 21 | 2.4615 | 0 | 4 | 2.4615 | 0 | 13.5 | 2.4615 | 2 | 26 | 2.4615 | 4 | 11 | 2.4615 | 4 | 12 | 2.4615 | 87.5 | 14.7692
2019-12-12 | 0 | 21 | 0 | 0 | 4 | 0 | 0 | 13.5 | 0 | 0 | 32 | 0 | 0 | 11 | 0 | 0 | 12 | 0 | 93.5 | 0
2019-12-13 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
Expected Total Hour | 32 |  |  | 32 |  |  | 32 |  |  | 32 |  |  | 32 |  |  | 32 |  |  | 192
Expected Hour per Day | 2.4615 |  |  | 2.4615 |  |  | 2.4615 |  |  | 2.4615 |  |  | 2.4615 |  |  | 2.4615 |  |  | 14.7692

## Tasks
Tasks/Features | Hours | Assign to | Actual | Impact | Ratio |  | Total
Flat File Logging Implementation and Testing | 32 | Michell | 0 | 0 |  | Michell | 32
AuthZ Implementation and Testing | 32 | Jacen | 0 | 0 |  | Jacen | 32
Data Store Logging Implementation and Testing | 32 | Jake | 0 | 0 |  | Jake | 32
Flat File Archiving Implementation and Testing | 32 | Albert | 24.5 | 24.5 |  | Albert | 32
AuthN Implementation and Testing | 32 | Peter | 6 | 6 |  | Peter | 32
Error Handling Implementation and Testing | 32 | Daniel | 0 | 0 |  | Daniel | 32
192
[6 empty] | Start Date | End Date
[6 empty] | 11-30-2019 | 2019-12-12
[6 empty] | velocity capacity | 52hrs / person
Total Velocity | 192 | Actual Hours | 30.5 | Impact | 30.5 | Actual/Planned | 84.11% | Impact/Planned | 84.11%

## KanBan Board
To Do | In progress | Testing | Blocked | Done
Flat File Logging Implementation and Design | Michell
AuthZ Implementation and Design | Jacen
Data Store Logging Implementation and Design | Joshua
Flat File Archiving Implementation and Design | Albert
AuthN Implementation and Design | Peter
Error Handling Implementation and Design | Daniel