## Work Hours
| Michell Kuang |  |  | Jacen Tan |  |  | Albert Du |  |  | Peter Park |  |  | Daniel Gione |  |  | Joshua McDaniel |  |  | Team Analysis
Hours Spent ¦ Hours Remaining | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Actual | Impact | Expected | Impact | Expected
2019-12-30 | 0 | 36 | 36 | 0 | 32 | 32 | 0 | 36 | 36 | 0 | 32 | 32 | 0 | 32 | 32 | 0 | 36 | 36 | 204 | 204
2019-12-31 | 0 | 36 | 34.2857 | 0 | 32 | 30.4762 | 2 | 34 | 34.2857 | 0 | 34 | 30.4762 | 0 | 34 | 30.4762 | 0 | 36 | 34.2857 | 206 | 194.2857
2020-01-01 | 2 | 34 | 32.5714 | 0 | 32 | 28.9524 | 1.5 | 32.5 | 32.5714 | 0 | 34 | 28.9524 | 0 | 34 | 28.9524 | 0 | 36 | 32.5714 | 202.5 | 184.5714
2020-01-02 | 1 | 33 | 30.8571 | 0 | 32 | 27.4286 | 2 | 31.5 | 30.8571 | 0 | 34 | 27.4286 | 0 | 34 | 27.4286 | 0 | 36 | 30.8571 | 200.5 | 174.8571
2020-01-03 | 0 | 33 | 29.1429 | 0 | 32 | 25.9048 | 2 | 30.5 | 29.1429 | 0 | 34 | 25.9048 | 0 | 34 | 25.9048 | 1 | 35 | 29.1429 | 198.5 | 165.1429
2020-01-04 | 0 | 33 | 27.4286 | 0 | 32 | 24.381 | 1.5 | 29 | 27.4286 | 0 | 34 | 24.381 | 0 | 34 | 24.381 | 0 | 35 | 27.4286 | 197 | 155.4286
2020-01-05 | 6 | 31 | 25.7143 | 0 | 32 | 22.8571 | 2 | 28 | 25.7143 | 0 | 34 | 22.8571 | 1 | 34 | 22.8571 | 4 | 31 | 25.7143 | 190 | 145.7143
2020-01-06 | 0 | 31 | 24 | 0 | 32 | 21.3333 | 1 | 27.5 | 24 | 0 | 34 | 21.3333 | 0 | 34 | 21.3333 | 0 | 31 | 24 | 189.5 | 136
2020-01-07 | 0 | 31 | 22.2857 | 0 | 32 | 19.8095 | 2 | 26.5 | 22.2857 | 0 | 34 | 19.8095 | 1 | 33 | 19.8095 | 2 | 29 | 22.2857 | 185.5 | 126.2857
2020-01-08 | 1 | 31 | 20.5714 | 0 | 32 | 18.2857 | 0 | 26.5 | 20.5714 | 0 | 34 | 18.2857 | 0 | 33 | 18.2857 | 0 | 29 | 20.5714 | 185.5 | 116.5714
2020-01-09 | 1 | 30 | 18.8571 | 0 | 32 | 16.7619 | 0 | 26.5 | 18.8571 | 0 | 34 | 16.7619 | 2 | 32 | 16.7619 | 2 | 27 | 18.8571 | 181.5 | 106.8571
2020-01-10 | 0 | 30 | 17.1429 | 0 | 32 | 15.2381 | 2 | 25.5 | 17.1429 | 0 | 34 | 15.2381 | 0 | 32 | 15.2381 | 0 | 27 | 17.1429 | 180.5 | 97.1429
2020-01-11 | 0 | 30 | 15.4286 | 0 | 32 | 13.7143 | 2 | 23.5 | 15.4286 | 0 | 34 | 13.7143 | 2 | 30 | 13.7143 | 1 | 26 | 15.4286 | 175.5 | 87.4286
2020-01-12 | 0 | 30 | 13.7143 | 0 | 32 | 12.1905 | 2 | 21.5 | 13.7143 | 1 | 33 | 12.1905 | 0 | 30 | 12.1905 | 0 | 26 | 13.7143 | 172.5 | 77.7143
2020-01-13 | 3 | 27 | 12 | 0 | 32 | 10.6667 | 2 | 19.5 | 12 | 1 | 32 | 10.6667 | 1 | 29 | 10.6667 | 2 | 24 | 12 | 163.5 | 68
2020-01-14 | 0 | 27 | 10.2857 | 0 | 32 | 9.1429 | 3 | 20.5 | 10.2857 | 1 | 31 | 9.1429 | 1 | 28 | 9.1429 | 0 | 24 | 10.2857 | 162.5 | 58.2857
2020-01-15 | 2 | 25 | 8.5714 | 0 | 32 | 7.619 | 0 | 20.5 | 8.5714 | 1 | 30 | 7.619 | 0 | 28 | 7.619 | 3 | 21 | 8.5714 | 156.5 | 48.5714
2020-01-16 | 0 | 25 | 6.8571 | 0 | 32 | 6.0952 | 1.5 | 19 | 6.8571 | 2 | 28 | 6.0952 | 4 | 25 | 6.0952 | 2 | 19 | 6.8571 | 148 | 38.8571
2020-01-17 | 3 | 22 | 5.1429 | 0 | 32 | 4.5714 | 2 | 17 | 5.1429 | 2 | 26 | 4.5714 | 6 | 22 | 4.5714 | 3 | 16 | 5.1429 | 135 | 29.1429
2020-01-18 | 2 | 21 | 3.4286 | 0 | 32 | 3.0476 | 0 | 17 | 3.4286 | 1 | 25 | 3.0476 | 4 | 19 | 3.0476 | 5 | 11 | 3.4286 | 125 | 19.4286
2020-01-19 | 8 | 15 | 1.7143 | 0 | 32 | 1.5238 | 2 | 15 | 1.7143 | 1 | 24 | 1.5238 | 6 | 13 | 1.5238 | 2 | 9 | 1.7143 | 108 | 9.7143
2020-01-20 | 6 | 12 | 0 | 0 | 32 | 0 | 2 | 13 | 0 | 8 | 16 | 0 | 5 | 10 | 0 | 4 | 5 | 0 | 88 | 0
2020-01-21 | SPRINT RETROSPECTIVE | [19 empty] | *To make it easier for graphing, this record how much work left.
Expected Total Hour | 36 |  |  | 32 |  |  | 36 |  |  | 32 |  |  | 32 |  |  | 36 |  |  | 204
Expected Hour per Day | 1.7143 |  |  | 1.5238 |  |  | 1.7143 |  |  | 1.5238 |  |  | 1.5238 |  |  | 1.7143 |  |  | 9.7143

## Tasks
Tasks/Features | Hours | Assign to | Actual | Impact | Ratio |  | Total
User Management Logging | 4 | Michell | 2 | 1 | 0.5 | Michell | 36
AuthZ Rework | 16 | Jacen | 0 | 0 | #DIV/0! | Jacen | 32
User Management Database | 26 | Jake | 24 | 16 | 0.66667 | Jake | 36
Registration(Normal User) | 26 | Albert | 19 | 16 | 0.84211 | Albert | 36
Create Account | 10 | Albert | 14.5 | 11.5 | 0.7931 | Peter | 32
Enable/Disable Account | 16 | Daniel | 14 | 11 | 0.78571 | Daniel | 32
Create User Session | 16 | Michell | 20 | 14 | 0.7
Data Masking Logging | 16 | Michell | 13 | 9 | 0.69231 | Start Date | End Date
Delete Account | 10 | Jake | 7 | 4 | 0.57143 | 12-31-2019 | 01-20-2020
Create System Admin | 16 | Jacen | 0 | 0 | #DIV/0!
Data Masking AuthN | 16 | Peter | 1 | 1 | 1 | velocity capacity | 40 | hrs/person
Update Account | 16 | Daniel | 20 | 13 | 0.65 |  | 240 | hrs total
AuthN Rework | 16 | Peter | 17 | 13 | 0.76471
Total Velocity | 204 | Actual Hours | 151.5 | Impact Hours | 109.5 | Actual/Planned | 25.74% | Impact/Planned | 46.32%

## KanBan Board
To Do | In progress | Testing | Blocked | Done
User Management Logging | Michell
AuthZ Rework | Jacen
User Management Database | Joshua
Registration(Normal User) |  |  |  | Albert
Create Account |  |  | Albert
Enable/Disable Account | Daniel
Create User Session | Michell
Data Masking Logging | Michell
Delete Account | Jake
Create System Admin | Jacen
Data Masking AuthN | Peter
Update Account | Daniel
AuthN Rework |  | Peter